## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Shaheen Begum | 2026-03-03 | Retrieved document chunks were not always relevant | Sprint 2 | Self | Logical | Improved retrieval with corrective RAG | 2026-03-04 | Closed | Retrieval relevance improved
2 | Shaheen Begum | 2026-03-05 | Generated answers did not include proper source citations for some responses | Sprint 3 | Self | Standards | Added source extraction logic | 2026-03-07 | Closed | Citation issue resolved
3 | Shaheen Begum | 2026-03-07 | Groq API key not loading in Reflex backend | Sprint 3 | Self | Logical | Fixed using CMD environment variable | 2026-03-10 | Closed | Fixed with set GROQ_API_KEY
4 | Shaheen Begum | 2026-03-12 | UI changes not reflecting after code update | Sprint 4 | Self | Maintainability | Deleted .web folder and did hard refresh | 2026-03-14 | Closed | Clean rebuild resolved
5 | Shaheen Begum | 2026-03-15 | Model selector dropdown not updating selected model correctly | Sprint 4 | Self | User Interface | Fixed state binding in ChatState | 2026-03-17 | Closed | Model switching now works properly
6 | Shaheen Begum | 2026-03-25 | Large PDF files take too much time to process | Sprint 4 | Self | Standards | Optimized chunking and embedding process | 2026-03-26 | Closed | Large file processing improved
7 | Shaheen Begum | 2026-03-27 | System crashes when user submits empty question | Sprint 5 | Self | Logical | Added validation to block empty queries | 2026-03-29 | Closed | Empty query handled safely
8 | Shaheen Begum | 2026-03-31 | Follow-up questions lose conversation context | Sprint 5 | Self | Logical | Improved history handling in ChatState | 2026-03-31 | Closed | Context maintained correctly
9 | Shaheen Begum | 2026-04-01 | Unsupported file formats not showing proper error message | Sprint 5 | Self | User Interface | Added clear error message for invalid files | 2026-04-01 | Closed | Error handling improved
10 | Shaheen Begum | 2026-04-02 | Clear Session button not clearing vector database | Sprint 5 | Self | Logical | Fixed clear_db() function | 2026-04-02 | Closed | Session reset working completely

## Sheet2
Logical
User Interface
Maintainability
Standards
Others